## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Admin | I want to collect data from different website | so to make a data set | 4 | somesh | 2018-09-22
1 | SB1/US2 | Admin | I want to filter the data | so to categorize the data | 2 | shubham | 2018-09-23
1 | SB1/US3 | Admin | I want to clean the data set | dividation of images | 2 | swinal | 2018-09-24
1 | SB1/US4 | Admin | I want to resize the images | convert them into size of 32X32 | 2 | swinal | 2018-09-30
1 | SB1/US5 | Admin | I want to crop the data set | so to get proper shaped images | 2 | shubham | 2018-01-10
| SB1/US6 | Admin | I want to apply data preproccessing | data is ready for application | 2 | somesh | 2018-05-10
| SB1/US7 | Admin | I want to create GUI | so to show my result | 2 | shubham | 2018-10-10
| SB1/US8 | ADmin | I want to apply text to speech feature | to get my result spoken | 2 | swinal | 2018-12-10
| SB1/US9 | Admin | I want to train the data set | to get the results | 2 | shubham | 2018-10-15
| SB1/US10 | Admin | I want to extract the features | to get only important part of images | 2 | swinal | 2018-10-20
| SB1/US11 | Admin | I want to remove the noises | to get more accurate results | 2 | somesh | 2018-10-25
| SB1/US12 | Admin | I want to detect parking signs | detect signs | 2 | somesh | 2018-10-26
| SB1/US13 | Admin | I want to test the trained data set | to check the ccuracy of my machine | 2 | shubham | 2018-10-27
| SB1/US14 | Admin | I want to apply algorithm for trianing the data set | to make the machine learn | 2 | swinal | 2018-10-27
| SB1/US15 | Admin | I want to combine the project with the gui | to get the graphical information | 2 | shubham | 2018-10-28
| SB1/US16 | Admin | I want to test the data with Trainning Datasets | to get the what accuracy is. | 2 | somesh | 2018-10-30
| SB1/US17 | Admin | I want to apply optimization algorithm | to increase the accuracy | 2 | shubham | 2018-11-05
| SB1/US18 | Admin | Test the GUI | to get the insight of GUI | 2 | swinal | 2018-11-10
| SB1/US19 | Admin | Combine the GUI with the model | to see how it looks | 2 | shubham | 2018-11-12
| SB1/US20 | Admin | Test the application in the real world | to see its applications. | 2 | somesh | 2018-11-15
| SB1/US21 | DBA
| SB1/US22 | DBA
| SB1/US23 | DBA
| SB1/US24 | DBA
DBA
DBA
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
HOD
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
Faculty
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
TPO
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
Transport
TUTOR
TUTOR
TUTOR
TUTOR
Timetable CO.
Timetable CO.
Timetable CO.
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Librarian
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Executive
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
Director
TA
TA
TA
TA
TA
Admin

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Data Gathering>
SB1/US1 | Admin | SB1/D1/T1 | I want to get the pictures from the internet | so to make a data set | Not Started
|  | SB1/D1/T2 | I want to check the size of the images | so to images of same size | Not Started | 2018-09-26
|  | SB1/D1/T3 | I want to now crop the images | so I can apply calculations | Not Started | 2018-09-27
|  | SB1/D1/T4 | I want to seprate image from the background | so to work only on main part | Not Started | 2018-09-30
|  | SB1/D1/T5 | I want to clean the image | so for accurate result | Not Started | 2018-10-05
|  | SB1/D1/T6 | I want to convert the image into grayscale | so it is easy to process | Not Started | 2018-10-06
SB1/US2 | Admin | SB1/D2/T1 | I want to partition the data into two sets | so for training and testing set | Not Started | 2018-10-12
SB1/D2/T2
SB1/D2/T3
SB1/D2/T4
SB1/D2/T5
SB1/US3 | Admin | SB1/D3/T1
SB1/D3/T2
SB1/D3/T3
SB1/D3/T4
SB1/US6 | Admin | SB1/D4/T1
SB1/D4/T2
SB1/D4/T3
SB1/D4/T4
SB1/D4/T5
SB1/US7 |  | SB1/D5/T1
SB1/D5/T2
SB1/D5/T3
SB1/D5/T4
SB1/US27 |  | SB1/D6/T1
SB1/D6/T2
SB1/D6/T3
SB1/D6/T4
SB1/D6/T5
SB1/US27 |  | SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/D7/T5
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/D9/T5
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/D10/T5
SB1/US53 |  | SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/D11/T5
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/D14/T5
SB1/US71 |  | SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/D15/T5
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 1 | 1 | Tasks
2018-09-12 | 2 | 1
2018-09-11 | 2 | 2
2018-09-14 | 1 | 1
2018-09-16 | 1 | 0
2018-09-18 | 1 | 2
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <GUI Creation>
| Creating GUI | SB2/D1/T1 | Creating basic using HTML | basic page | not started | 2018-10-14
|  | SB2/D1/T2 | Adding Css to it | get some stylling | not started | 2018-10-15
|  | SB2/D1/T3 | addng basic homepage | for navigation | not started | 2018-10-16
| Creating Upload Button | SB2/D2/T1 | Adding Test button | to check for image | not started | 2018-10-17
SB2/D2/T2
SB2/D2/T3
SB2/D2/T4
SB2/D2/T5
| TA Receiving Confirmation Email | SB2/D3/T1
SB2/D3/T2
SB2/D3/T3
SB2/D3/T4
| Register TO into the application(using poornima email account) | SB2/D4/T1
SB2/D4/T2
SB2/D4/T3
SB2/D4/T4
SB2/D4/T5
| TO Receiving Confirmation Email | SB2/D5/T1
SB2/D5/T2
SB2/D5/T3
SB2/D5/T4
| Add Subject | SB2/D6/T1
SB2/D6/T2
SB2/D6/T3
SB2/D6/T4
SB2/D6/T5
| Register Timetable Co-ordinator into the application | SB2/D7/T1
SB2/D7/T2
SB2/D7/T3
SB2/D7/T4
SB2/D7/T5
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1
SB2/D8/T2
SB2/D8/T3
|  | SB2/D8/T4 |  | RA+SP+PB+RM

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 1 | 0 | Tasks
2017-09-28 | 1 | 2
2017-10-02 | 1 | 1
2017-10-05 | 1 | 1
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Training Model>
| Checking Algorithm | SB3/D1/T1 | Check for which algorith to apply | it optimized | not started | 2018-10-20
|  | SB3/D1/T2 | Searching for libraries | to work on | not started | 2018-10-21
[5 empty] | not started | 2018-10-22
| Apllying Algorithm | SB3/D2/T1 | Applying input image | for proccessing | not started | 2018-10-24
|  | SB3/D2/T2 | Choosing parameter to apply | for filtration | not started | 2018-10-26
|  | SB3/D2/T3 | Perform pooling to reduce dimenstionality size | to get in dimension | not started | 2018-10-28
| Test and Modify | SB3/D3/T1 | Test the layers of CNN | to check if results | not started | 2018-10-30
|  | SB3/D3/T2 | Apply more layers if required | to increase accuracy | not started | 2018-11-02
| Reapply | SB3/D4/T1 | Flatten the output feed into fully connected layer | to get the insight | not started | 2018-11-05

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 2 | 1 | Tasks
2018-10-18 | 1 | 1
2018-10-20 | 2 | 1
2018-10-21 | 2 | 2
2018-10-22 | 1 | 1
2018-10-23 | 0 | 0
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Integration>
| Aggregating GUI and Model | SB4/D1/T1 | Integrating the GUI with the trained Model | to give an platform | Not Started | 2018-12-06

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days